## SprintInfo
Start Date | 2020-02-03 | Enter the start date for the sprint
End Date | 2020-02-24 | Enter the ending date for the sprint
Elapsed Days | 16
Holidays | 1 | If there are any holidays or other special days occuring during the sprint, enter that number here
Working Days | 15
Number of Devs | 5
Utilization | 70% | Enter a value for the utilization of the team
Available Dev Hours | 210
Daily Dev Hours | 13.125

## BacklogTable
Sprint | Item ID | Estimated Hours | Task Name | Assigned To | Remaining Hours | Status
1 | 1 | 30 | Web front | Vinícius | 0 | Completed
1 | 2 | 70 | Web back | David | 0 | Completed
1 | 3 | 5 | Web front + back | Vinícius | 4 | In Progress
1 | 4 | 120 | Mobile | David | 20 | In Progress
| 5 |  |  |  | 0
| 6 |  |  |  | 0
| 7 |  |  |  | 0
| 8 |  |  |  | 0
| 9 |  |  |  | 0
| 10 |  |  |  | 0
Total |  | 225 |  |  | 24

## BurnDownTable
Work Day | Target Burn Down | Forecast Burn Down | Actual Burn Down
0 | 225 | 225 | 225
1 | 210 | 211.875 | 220
2 | 195 | 198.75 | 190
3 | 180 | 185.625 | 170
4 | 165 | 172.5 | 160
5 | 150 | 159.375 | 155
6 | 135 | 146.25 | 90
7 | 120 | 133.125 | 85
8 | 105 | 120 | 50
9 | 90 | 106.875 | 30
10 | 75 | 93.75 | 24
11 | 60 | 80.625 | 10
12 | 45 | 67.5 | 5
13 | 30 | 54.375 | 0
14 | 15 | 41.25 | 0
15 | 0 | 28.125 | 0
Note on A2: PowerUps for Excel: Create one row per day in the sprint.